## Team
Initials | First | Last | Email | GitHub Username
ykw | Yikan | Wang | ywang463@stevens.edu | Xander Wang
lwk | Lingwen | Kong | lkong11@stevens.edu | konglingwengit
hyz | Hengyuan | Zhang | hzhan56@stevens.edu | hygithub3901
myl | Muyang | Li | mli89@stevens.edu | mujiuzhou-007
|  |  | GitHub Repository: | https://github.com/konglingwengit/SSW-555-A-Project-3/

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | hyz | Done
1 | US02 | Birth before marriage | hyz | Coding
1 | US03 | Birth before death | myl | Coding
1 | US10 | Marriage after 14 | ykw | Coding
1 | US11 | No bigamy | ykw | Coding
1 | US06 | Divorce before death | myl | Coding
1 | US07 | Less then 150 years old | lwk | Done
1 | US29 | List deceased | lwk | Done
2 | US30 | List all living married people | lwk | plan
2 | US15 | sibling count | lwk | plan

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2021-03-04 | 42 |  | 0
2021-03-18 | 38 | 4 | 330 | 180 | 110

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | hyz | Done | 100 | 60 | 90 | 70 | 2021-03-03 | Review Results
T01.01 | Store read file date | hyz | [6 empty] | Keep doing:
T01.02 | Store current date | hyz | [6 empty] | Keep updating repository with new work
T01.03 | Compare read date and current date | hyz
US02 | Birth before marriage | hyz | Coding | 100 | 60 |  |  |  | Avoid:
Try not to use old versions of github to add new functions
T02.01 | Store birth date | hyz | Done | [5 empty] | Please don't enter act time in stories steps
T02.02 | Store marriage date | hyz
T02.03 | Compare birth date and marriage date | hyz
Total Actual minutes spend on
US07 | Less then 150 years old | lwk | done | 100 | 70 | 95 | 50 | 2021-03-03 | 180
T03.01 | getting all birth date | lwk | done | 50 | 30 | 45 |  | 2021-03-03
T03.02 | Compare to current date | lwk | done | 50 | 40 | 50 |  | 2021-03-03
US29 | List deceased | lwk | done | 100 | 70 | 90 | 60 | 2021-03-03
T029.01 | Check DEAT status | lwk | done | 50 | 30 | 45 |  | 2021-03-03
T029.02 | Append object on list | lwk | done | 50 | 40 | 45 |  | 2021-03-03
US10 | Check marriage if before 14 | WYK | coding | 50 | 50
US11 | check if marry twice at same time | WYK | coding | 50 | 50
US03 | Birth before death | myl | coding | 100 | 60
T03.01 | Store birth date | myl | Done
T03.02 | Store death date | myl | Done
T03.02 | Compare to birth date and death date | myl
US06 | Divorce before death | myl | Coding | 150 | 80
T06.01 | Store divorce date | myl
T06.02 | Store death date | myl
T06.03 | Cpmpare to divorce date and death date | myl
US30 | List all living married people | lwk | Coding | 100 | 70
T30.01 | Planning | lwk
US15 | sibling count | lwk | Coding | 100 | 80
T30.01 | Planning | lwk