## Team
Initials | First | Last | Email | GitHub Username
ykw | Yikan | Wang | ywang463@stevens.edu | Xander Wang
lwk | Lingwen | Kong | lkong11@stevens.edu | konglingwengit
hyz | Hengyuan | Zhang | hzhan56@stevens.edu | hygithub3901
myl | Muyang | Li | mli89@stevens.edu | mujiuzhou-007
hyl | Haoyu | Li | hli109@stevens.edu | hahahakkkE7
|  |  | GitHub Repository: | https://github.com/konglingwengit/SSW-555-A-Project-3/

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | hyz | Done
1 | US02 | Birth before marriage | hyz | Done
1 | US03 | Birth before death | myl | Done
1 | US06 | Divorce before death | myl | Done
1 | US07 | Less then 150 years old | lwk | Done
1 | US10 | Marriage after 14 | ykw | Done
1 | US11 | No bigamy | ykw | Done
1 | US14 | Multiple births <=5 | hyl | Done
1 | US16 | Male last names | hyl | Done
1 | US29 | List deceased | lwk | Done
2 | US05 | Marriage before death | hyz | Done
2 | US08 | Birth before marriage of parents | myl | Done
2 | US15 | sibling count | lwk | Done
2 | US19 | First cousins should not marry | hyl | Done
2 | US20 | Aunts and uncles | hyl | Done
2 | US22 | Unique IDs | ykw | Done
2 | US23 | Unique name and birth date | ykw | Done
2 | US30 | List all living married people | lwk | Done
2 | US42 | Reject illegitimate dates | myl | Done
3 | US04 | Marriage before divorce | lwk | Done
3 | US12 | Parents not too old | hyz | Done
3 | US13 | Siblings spacing | hyz | Done
3 | US18 | Siblings should not marry | myl | Done
3 | US24 | Unique families by spouses | YKW | Done
3 | US25 | Unique first name in families | YKW | Done
3 | US34 | List large age difference | lwk | Done
3 | US35 | List recent births | myl | Done
3 | US36 | Listdeath | YKW | Done
3 | US37 | list survivors | YKW | Done
4 | US31 | List living single | hyz | Done
4 | US33 | List orphans | myl | Done
4 | US38 | List upcoming birthdays | hyz | Done
4 | US39 | List upcoming anniversaries | lwk | Done
4 | US41 | Include partial dates | myl | Done
4 | US40 | Include input line numbers | hl | Done
4 | US17 | No marriages to children | hl | Done
4 | US21 | Correct gender for role | hl | Done
4 | US26 | Corresponding entries | hl | Done
4 | US27 | Include individual ages | hl | Done
4 | US28 | Order siblings by age | hl | Done
4 | US32 | List multiple births | hl | Done
4 | US09 | Birth before death of parents | hl | Done

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Sprint1 | 2021-03-04 | 42 |  | 0
| 2021-03-18 | 38 | 4 | 330 | 180 | 110
| 2021-03-22 | 32 | 6 | 390 | 100 | 36
Sprint2 | 2021-03-31 | 23 | 9 | 310 | 270 | -17.7778
Sprint3 | 2021-04-13 | 13 | 10 | 105 | 220 | 0.47727
Sprint4 | 2021-04-26 | 0 | 13 | 1069 | 1100 | 0.97182

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | hyz | Done | 100 | 60 | 23 | 70 | 2021-03-17 | Review Results
Our speed is slow but we are hopeful to complete all stories soon
T01.01 | Store read file date | hyz | [6 empty] | Keep doing:
T01.02 | Store current date | hyz | [6 empty] | Keep updating repository with new work
T01.03 | Compare read date and current date | hyz
US02 | Birth before marriage | hyz | Coding | 100 | 60 | 24 |  | 2021-03-17 | Avoid:
Try not to use old versions of github to add new functions
T02.01 | Store birth date | hyz | Done | [5 empty] | Please don't enter act time in stories steps
T02.02 | Store marriage date | hyz
T02.03 | Compare birth date and marriage date | hyz
Total Actual minutes spend on
US07 | Less then 150 years old | lwk | done | 100 | 70 | 32 | 50 | 2021-03-03 | 340
T03.01 | getting all birth date | lwk | done
T03.02 | Compare to current date | lwk | done
US29 | List deceased | lwk | done | 100 | 70 | 25 | 60 | 2021-03-03
T029.01 | Check DEAT status | lwk | done
T029.02 | Append object on list | lwk | done
US10 | Check marriage if before 14 | WYK | done | 50 | 50
US11 | check if marry twice at same time | WYK | done | 50 | 50 | 42 | 50 | 2021-03-27
US03 | Birth before death | myl | coding | 100 | 60 | 40 | 60
T03.01 | Store birth date | myl | Done
T03.02 | Store death date | myl | Done
T03.02 | Compare to birth date and death date | myl
US06 | Divorce before death | myl | Coding | 150 | 80 | 60 | 50
T06.01 | Store divorce date | myl
T06.02 | Store death date | myl
T06.03 | Cpmpare to divorce date and death date | myl

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US08 | Birth before marriage of parents | myl | Done | 80 | 60 | 60 | 70 | March 31,2021 | Review Results
The final work of Sprint1 has been completed, and the code of Sprint2 user stories is being written and tested.
T08.01 | store children's birth date | myl | [6 empty] | Keep doing:
T08.02 | store parents's marriage date | myl | [6 empty] | Hold team meetings on time, exchange code, fix bugs, and plan for the next step.
T08.03 | compare children's birth date and parents's marriage date | myl
T08.04 | not more than 9 months after their divorce | myl
Avoid:
US42 | Reject illegitimate dates | myl | Done | 100 | 60 | 40 | 50 | March 31,2021 | Conflicting team assignments
Incorrect test results
T42.01 | store birth date and death date | myl
T42.02 | store marriage date and divorce date | myl
T42.03 | Verify that all dates are in the correct format | myl | [6 empty] | Total Actual minutes spend on：
325
US30 | List all living married people | lwk | done | 30 | 70 | 50 | 45 | Mar31，2021
T30.01 | Planning | lwk
US15 | sibling count | lwk | done | 25 | 80 | 60 | 55 | Mar31,2021
T30.01 | Planning | lwk
US22 | Unique ids | YKW | done | 25 | 35 | 50 |  | Mar31,2021
US23 | unique birthday | YKW | done | 25 | 35 | 50 | 50 | Mar31,2021

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | LOC_Total | TIME_Total | Review Results
US18 | Siblings should not marry | myl | Done | 15 | 60 | 15 | 50 | 2021-04-13 | 105 | 220 | Our speed is slow but we are hopeful to complete all stories soon
Keep doing:
T18,01 | Find all the kids | myl | [8 empty] | Keep updating repository with new work
T18.02 | find which are siblings | myl
T18.03 | Siblings should not marry | myl
Avoid:
Try not to use old versions of github to add new functions
US35 | List recent births | myl | Done | 15 | 60 | 15 | 60 | 2021-04-13 |  |  | Please don't enter act time in stories steps
T38.01 | List all people | myl
T38.02 | List all people in a GEDCOM file who were born in the last 30 days | myl
US34 | List large age difference | lwk | Done | 15 | 120 | 15 | 40 | 2021-04-13
T34.01 | List large age difference | lwk
T34.02 | List all people in a GEDCOM file who are spouses with large age difference | lwk
US04 | marriage before divorce | lwk | Done | 15 | 120 | 15 | 25 | 2021-04-13
T04.01 | marriage before divorce | lwk
T04.02 | List all people in a GEDCOM file with marriage before divorce | lwk
US12 | Parents not too old | hyz | Done | 25 | 150 | 25 | 35 | 2021-04-15
T12,01 | Find a family with husband, wife and child | hyz
T12.02 | Find the birth date of them | hyz
T12.03 | Compare their birth date | hyz
US13 | Siblings spacing | hyz | Done | 20 | 150 | 20 | 10 | 2021-04-15
T13,01 | Find all children in every family | hyz
T13,02 | Find the children birth date and put in a list | hyz
T13,03 | Sort the list | hyz
T13,04 | Compare every two brith date in the sorted list | hyz

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | LOC_Total | TIME_Total
US33 | List orphans | myl | Done | 100 | 60 | 40 | 19 | 2021-04-26 | 89 | 66
T33.01 | List all people | myl
T33.02 | List the cildren who lost their parents | myl
Review Results
US41 | Include partial dates | myl | Done | 100 | 60 | 20 | 20 | 2021-04-26 | Our speed is slow but we are hopeful to complete all stories soon
Keep doing:
T41.01 | List all people and family | [7 empty] | Keep updating repository with new work
T41.02 | find all the birthday, deathday, marriageday, divorceday | myl
T41.03 | Whether the comparison date is a canonical date | myl
Avoid:
US42 | Reject illegitimate dates | lwk | Done | 130 | 90 | 15 | 2 | 2021-04-28 | Try not to use old versions of github to add new functions
Please don't enter act time in stories steps
T42.01 | Get error list | lwk
US39 | List upcoming anniversaries | lwk | Done | 100 | 75 | 14 | 25 | 2021-04-28
T39.01 | calculate date
US38 | List upcoming birthdays | hyz | Done | 130 | 90 | 100 | 70 | 2021-04-28
T38.01 | calculate the date | hyz | Done
T38.02 | compare the date and birth in GED | hyz
T38.03 | add the satisfactory into a list | hyz
US31 | List living single | hyz | Done | 130 | 90 | 100 | 80 | 2021-04-28
T31.01 | calculate the birth date | hyz
T31.02 | find the 30 years old people who have no marriage | hyz
T31.03 | add the satisfactory into a list | hyz
US33 | List orphans | myl | Done | 100 | 90 | 60 | 70 | 2021-04-28
US38 | List upcoming birthdays | hyz | Done | 100 | 90 | 70 | 80 | 2021-04-28
US39 | List upcoming anniversaries | lwk | Done | 100 | 90 | 65 | 65 | 2021-04-28
US41 | Include partial dates | myl | Done | 100 | 90 | 70 | 65 | 2021-04-28
US40 | Include input line numbers | hl | Done | 100 | 90 | 100 | 80 | 2021-04-28
US17 | No marriages to children | hl | Done | 100 | 90 | 60 | 77 | 2021-04-28
US21 | Correct gender for role | hl | Done | 100 | 90 | 65 | 77 | 2021-04-28
US26 | Corresponding entries | hl | Done | 100 | 90 | 70 | 80 | 2021-04-28
US27 | Include individual ages | hl | Done | 100 | 90 | 80 | 60 | 2021-04-28
US28 | Order siblings by age | hl | Done | 100 | 90 | 50 | 90 | 2021-04-28
US32 | List multiple births | hl | Done | 100 | 90 | 50 | 50 | 2021-04-28
US09 | Birth before death of parents | hl | Done | 100 | 90 | 40 | 90 | 2021-04-28